### 3. Substantive gaps in the policy

I've ordered these roughly by how likely they are to cause a problem in practice.

A. No size tiering — this is the one most likely to break the process. A small project or enhancement and a organization-wide platform both go through four gates with ITC review at each. Departments will route around it. Recommend a two or three tier model: a lite path (single combined gate, IT-approved) below a defined cost/effort threshold, standard PTX above it, and a major tier requiring BAPS Inc. leadership.

B. ITC has no decision SLA. Departments have obligations at every gate; ITC has none. Add a meeting cadence, a decision turnaround (e.g. within one ITC cycle of a complete submission), and an auto-escalation if a decision slips. Without this, "the policy is slowing us down" becomes the standing complaint.

C. The support model is genuinely unclear (Dharmaketu's comment 4 isn't resolved). §3 says operational business-side support sits with Departments; §4.4 says IT transitions to a "production support group" after hypercare. Those aren't reconciled. Define a support tier model — who handles L1 user how-to questions, L2 functional configurations, L3 technical — and define hypercare duration and its exit criteria.

D. Gate 4.2 and 4.3 overlap. §4.1 grants approval to proceed to requirements definition. §4.2 is titled "Permit to Design, Estimate, and Plan" but its body describes requirements elicitation, then grants approval to proceed to design and planning. §4.3 then says IT produces the technical design — which 4.2 just authorized — and grants approval to build. The naming is effectively off by one. Either rename 4.2 to "Permit to Define Requirements" or move the design work explicitly into 4.3's pre-work.

E. P0 classification doesn't say what P0 gets you. §8 explains how ITC decides, but not the consequence. Does a P0 skip gates? Jump the queue? Get dedicated resources? If a P0 still walks all four gates at normal speed, the label is meaningless. Also missing: priority tiers below P0 (P1/P2/P3) and any published view of the backlog.

F. The 5% variance rule is under-specified. 5% of which baseline — original or most recently re-approved? Cumulative across changes or per change? 5% of timeline on a 12-month project is 18 days, which is very tight. Suggest: cost threshold = greater of 5% or a fixed dollar floor, tracked cumulatively; separate, looser threshold for schedule. This is also where Satyanishth's cost-cap idea (comment 24) should land — the two mechanisms need to be merged, not stacked.

G. Contingency (40% / 20% / 10%) is stated but not governed. Who owns it? Is it drawn down with approval or automatically available? Does consuming contingency count toward the 5% change threshold? Right now a project could burn 40% contingency with no change request at all.

H. No ITC charter details. Composition, quorum, how decisions are made (consensus or vote), delegation when members are unavailable, and conflict-of-interest handling are all undefined for a body that holds sole discretion over prioritization and P0.

I. No Department appeal path. §8 gives ITC sole discretion; §10 (with "reject" struck) gives ITC broad authority. There's no route for a Department that disagrees. Add a defined escalation to BAPS Inc. leadership with criteria.

J. Vendor / third-party procurement is entirely absent. Many projects will be SaaS or vendor-delivered. No gate covers vendor selection, contract and licensing review, data processing terms, security assessment of the vendor, or exit/data-portability. Recommend adding this to §4.2's assessment list and a vendor clause in §3.

K. Funding source is never addressed. Department budget or central IT budget? What happens when an approved project crosses a fiscal-year boundary or exceeds available funds? §11 gives ITC "review of budgets" but no funding model sits underneath it.

L. No benefits realization. §7 requires business value and expected benefits at intake, but nothing ever checks whether they materialized. Add a fifth gate or a post-implementation review at 60–90 days, reported to ITC. This also creates the feedback loop that makes future estimates better.

M. Data governance is thin — Satyanishth's comment 13 points at this. Beyond adding those terms, consider donor/devotee PII handling, retention, and the fact that this policy spans multiple jurisdictions (the reviewers are in Melbourne, Chicago, and Houston). Cross-border data handling deserves at least a sentence.

N. Volunteer resourcing isn't acknowledged. The policy assumes assignable IT resources with predictable capacity. In practice a significant share of delivery capacity is likely volunteer. Nothing covers what happens when a resource becomes unavailable mid-build, or how capacity is realistically forecast at the Permit to Build gate. This may be the biggest gap between the policy as written and how delivery actually goes.

O. No emergency / event-driven fast path. §12 allows exceptions "approved by ITC" with no criteria or timeline. Festival and event deadlines are immovable and real. Without a defined compressed path, urgent work will simply bypass the policy — and once that happens once, it happens routinely.

P. Missing artifacts. Both comments 0 and 15 are really asking for this. The memo references but doesn't attach: the project questionnaire, proposal template, change request form, PTX approval record, UAT sign-off, and rollout readiness checklist. List them as appendices with named owners and dates.

Q. No RACI (Ashish's comment 20). A gate-by-gate RACI table would resolve several of the ambiguities above at once — particularly the IT vs Department support question and who approves rollout.

R. Rollout approval is inconsistent with the other gates. ITC approves gates 1–3; §4.4 says rollout readiness comes jointly from IT RGC and the Department, with ITC absent. Deliberate or an oversight? State it either way.

S. No metrics or policy review cadence. Add a small set of KPIs (gate cycle time, estimate accuracy, change request volume, % delivered to approved cost) and commit to reviewing the policy itself annually.

### 4. Editorial fixes

- §3, para 1 is a sentence fragment: "All resources including development, architecture… and deployment." — no verb.

- §7 heading line has unbalanced parentheses: All projects (New (application/platform/system capability) /Existing (new phase/major feature).

- §12: "returned for reprioritized" → "returned for reprioritization."

- §11, IT RGC: three unlabeled paragraphs follow the bolded role name; a reader can't tell whether they all belong to IT RGC. Merge or sub-label.

- §6: bullet punctuation is inconsistent (some end with periods, most don't).

- §4.2: "Department SME(s) are requested to elicit requirements" — in a governance policy this should be "must" or "are responsible for."

- Add a definitions section. PTX, ITC, IT RGC, BA, PM, SME, MVP, POC, UAT, hypercare, and especially P0 vs S0 — which is exactly what Dharmaketu was after in comment 22.

- Versioning: "Draft v1.0" should be v0.x until approved, with a revision history table showing reviewers and dates.

### 5. Suggested next steps

- Get a decision on the struck-through "Reject the change request" line — it changes what §10 means.

- Route the draft back to Satyanishth Swami; his entire August 1 round is unanswered.

- Put dates and owners on the two open drafting actions (the IT process doc and the change request process) — both currently sit with Sandip Patel / Ashish Trivedi with no deadline.

- Add the tiering model (gap A) and the ITC decision SLA (gap B) before publishing. These two determine whether the policy is used or bypassed.

- Reset the effective date and add a transition clause for in-flight projects.

- Resolve or reply to all 26 comments in Word so the next version has a clean margin.

If it's useful, I can turn this into a Word document you can circulate, or produce a marked-up version of the memo itself with these as tracked changes and comments.